# INTRODUCTION TO CEMPS’S TRAINING PROGRAMME FOR THE YEAR-2 OF THE BASIS PROJECT

# In the year-1 of the Basis project, CEMP has engaged with 43 BME community organisations in West Sussex promoting Basis’s Infrastructure development Project, from which 29 BME organisations and 10 volunteers have been capacity built, using Infrastructure Development Training Programme.

# Continued monitoring and assessment of organisations progress and during the year-1 of the project, participant of the trainings sessions have asked for additional training provision and development support. These participants and community members have also asked for help to improve access to services. Thus extensive capacity building training programme and engagement with communities and service providers have been incorporated in this work programme to meet these identified needs and gaps.

# We are very fortunate that we have three highly experienced training consultants who are specialist in their field and are able to deliver year-2 training programme to enhance the abilities of marginalised communities and provide long term sustainability. This training programme is publicised on CEMP’s website and within other BME organisations and at the various community’s events.

# There is great deal of specialist work required to be delivered within the BME community organisation and members and CEMP has been very effective delivering this work under the Basis project thus building communities empowerment, confidence and trust.

# CEMP’s Basis Work Programme Year-2- From August 2010 July 2011

# Developing Infrastructure of BME communities in West Sussex

| Month | Development of Focus Groups | Community Development Infrastructure level-1 | Specialist Funding Training/ Workshops | Leadership- Management & Governance Infrastructure level-2 |
| --- | --- | --- | --- | --- |
| August 2010 | 1] Develop focus groups and volunteering within the 3 community organisations. 2] Assess Development support needs and identify any barriers. | Planning of training by working with training consultant and community groups | Planning of training by working with training consultant and community groups |  |
| Sept 2010 | 1] Develop focus groups and volunteering within the 3 community organisations. 2] Assess Development support needs and identify any barriers. |  | Northdown West Sussex Location: Crawley By Sandra Lamont Assessment and discussions with participants and evaluation of training session |  |
| October 2010 | 1] Develop understanding within focus groups of Organisations Purpose and Objectives. 2] Understanding distributed leadership |  |  |  |
| November 2010 | 1] Develop understanding within focus groups of Organisations Structures and Cultures. 2]Understanding distributed leadership 3] Community network meeting of 5-7 BME organisations | Northdown West Sussex Location: Crawley By John De Groot Assessment and discussions with participants and evaluation of training session | Coastal-Strip Area West Sussex Location: Goring by Sea by Sandra Lamont Assessment and discussions with participants and evaluation of training session |  |
| December 2010 | 1] Develop understanding within focus groups of Organisations Structures and Cultures. 2] Assess development support needs and identify barriers. | Coastal-Strip Area West Sussex Location Littlehampton By John DeGroot Assessment and discussions with participants and evaluation of training session Food Safety Certificate Northdown West Sussex Location: Crawley By William Wood | Northdown West Sussex Location: Crawley By Sandra Lamont Assessment and discussions with participants and evaluation of training session |  |
| January 2011 | 1] 2 Provide support to 2 focus groups to speak at CEMP AGM 2] Working with 3 focus groups understanding organisations structures and cultures. | Coastal -Strip Area – West Sussex Location Littlehampton By John De Groot 29th January 2011 Time: 11:00am-2:00pm Assessment and discussions with participants and evaluation of training session | Coastal-Strip Area West Sussex Location Littlehampton by Sandra Lamont Assessment and discussions with participants and evaluation of training session |  |
| February 2011 | 1] Work with 3 focus groups developing motivation and volunteering 2] Understanding distributed leadership | Coastal - Strip Area – West Sussex Location ----------- By John De Groot 26th February 2011 Time: 11:00am-2:00pm Assessment and discussions with participants and evaluation of training session | Coastal-Strip Area West Sussex Location Littlehampton by Sandra Lamont 12th February 2011 Time: 11:00am-2:00pm Assessment and discussions with participants and evaluation of training session | Northdown West Sussex Location---Crawley By Dr Richard Kay 28th February 2011 Moved to 5th March 2011 Time: 10:00-1:00pm Assessment and discussions with participants and evaluation of training session |
| March 2011 | 1] Working with 3 focus groups understanding organisations structures and cultures. 2] Understanding distributed leadership | Coastal - Strip Area – West Sussex Location ----------- By John De Groot 26th March 2011 Time: 11:00-2:00pm Assessment and discussions with participants and evaluation of training session | Northdown West Sussex Location----Crawley By Sandra Lamont 26th March 2011 Time: 10:00am-1:00pm Assessment and discussions with participants and evaluation of training session | Coastal-Strip Area West Sussex Location--------- By Dr Richard Kay 12th March 2011 Time: 11:00-2:00pm Assessment and discussions with participants and evaluation of training session |
| April 2011 | 1] Develop understanding within focus groups of Organisations Purpose and Objectives. 2] Understanding distributed leadership | Northdown West Sussex Location---Crawley by John De Groot 16th April 2011 Time: 10:00-1:00pm Assessment and discussions with participants and evaluation of training session | Coastal Strip – Area – West Sussex Location:------- By Sandra Lamont 9th April 2011 11:00am-2:00pm Assessment and discussions with participants and evaluation of training session |  |
| May 2011 | 1] Working with 3 focus groups understanding organisations purpose and objectives s 2] Understanding distributed leadership | Coastal - Strip Area – West Sussex Location ----------- By John De Groot 14th May 2011 11:00am-2:00pm Assessment and discussions with participants and evaluation of training session |  | Northdown West Sussex. Location---Crawley By Dr Richard Kay 28th May 2011 Time: 10:00-1:00pm Assessment and discussions with participants and evaluation of training session |
| June 2011 | 1] Working with 3 focus groups understanding organisations structures and cultures 2] Understanding distributed leadership | Northdown West Sussex Location---Crawley by John De Groot 25th June 2011 Time: 10:00am-1:00pm Assessment and discussions with participants and evaluation of training session | Coastal Strip – Area – West Sussex Location-------------- By Sandra Lamont 18th June 2011 11:00am-2:00pm Assessment and discussions with participants and evaluation of training session | Coastal-Strip Area West Sussex Location--------- By Dr Richard Kay 25th June 2011-02-16 11:00am-2:00pm Assessment and discussions with participants and evaluation of training session |
| July 2011 | 1] Working with 3 focus groups understanding organisations structures and cultures 2] Understanding distributed leadership | Coastal - Strip Area West Sussex Location------------- By John De Groot 9th July 2011 11:00am-2:00pm Assessment and discussions with participants and evaluation of training session | Northdown West Sussex Location---Crawley By Sandra Lamont 23rd July 2011 Time: 10:00-1:00pm Assessment and discussions with participants and evaluation of training session |  |

For further details and information about Infrastructure Development Training Programme , please

contact CEMP office:  Telephone : 01293 657030/657031/657033

Email: info@cemp.org.uk

Sharafat Hussain  Managing the Basis Project for all 4 partners and North and Coastal Strip Area

Temba Chofamba for Northdown West Sussex: 07779323175 : Email: Temba@cemp.org.uk

Henna Chowdhury for Coastal Strip Area West Sussex: 07501721183:  henna@bme-cs.org.uk